CYDD Mentorship project

RATIONALE  FOR  THE  PROJECT

In Turkey, the ratio of employment for the university graduates by April 2011 is %85.2 for male and %71.3 for female graduates (TUIK  April  2011).  Also according to EU 2011 education report; Turkey allocates only 2.86 % of  its GDP  for education. The percentage of youth leaving education between ages 18 - 24 is 44.3  (this ratio is 14.4% for EU).  In Turkey the ratio of university graduates versus general population is 14.7% (EU 40%).

The university student receiving  scholarship has come from  an economically disadvantaged family and/or area  to the big city for university education,  who needs  further support to overcome the problems to be faced, needs support for his/her personal development and guidance to make decisions and right choices toward  a good career and life.

CYDD  therefore  decided  to provide mentoring  support  along with scholarship through   a centralized and sustainable infrastructure  with monitoring standards and measurement methods .

Mentoring  project is intended to also make use of  CYDD alumni  as mentors  and  will make them part of a social responsibility project and will provide them leadership experience in return

GOAL OF THE PROJECT

CYDD  as  a well established NGO in the education field, has to date mainly focused its activities on Scholarship programs and supportive infrastructural projects. With this Project CYDD would like to move into a new field, setting up a one to one Mentorship program for their University Scholars.

Program  pursues  three  main  objectives:

-to provide CYDD ‘s “scholars” at University level with personal, sound and knowledgeable guidance for a successful start of their professional career and self -development.

-to strengthen  CYDD’s network of alumni by engaging them  in a social responsibility project where- by  they can have impact on the lives of young adults from  a similar background.

-to further institutionalize CYDD’s own organization through implementation of a specifically funded project.

PROJECT BENEFICIARIES

-University students , both male and female, who are receiving scholarship  from CYDD.

- Branch Office youth leaders: They will acquire a more professional approach for continuing their informal activities toward supporting youth in their personal development.

- “Alumni” Group: People who have received university scholarship from  CYDD in the past  and  working at least for 3 years,.

-CYDD branches will have a sustainable tool to keep in contact with the grantees and alumni

-CYDD  Headquarters : will  standardize and  monitor mentorship  activities in all participating  branches and  will gain  new  and potential members  to  continue  growing.

MAIN STAGES OF PROGRAM IMPLEMENTATION

-Team building

-Mentee-Mentor Program Building

-Announcement  of the program and branch selection

-Mentor-mentee  applications, interviews, training and matching

- Mentor-mentee program  implementation

-Train the trainee program  (to develop  mentor leaders and   trainers)

- Evaluation meetings,  surveys and reporting

- Communication

PROJECT RESULTS

-20 Branches (İstanbul, Ankara, İzmir, Bursa, İzmit  branches)

-202 mentors (70 alumni and 132 volunteer; 72 % female)

-202 mentee   (%68 female)

-Alumni database implementation started (3000 alumni on record)

-A web platform being developed.

-9 mentor trainers and 6 new mentor leaders available.

SOME MENTOR AND MENTEE OUTPUTS

Selected comments of mentors

Chance to learn that a relationship needs to be managed with mutual understanding and patience”

“I am glad to be of tangible benefit to CYDD”

“Contributed to my leadership capabilities”

“Taught me to take on responsibility and listen”

“A nice fellow traveller, empathy, sincerety and responsibility.”

“Someone waiting for me and I am waiting for someone to communicate.”

Selected comments of mentees

Enabled me  to think about the other person when I am listening or telling something.

Peace, optimism, confidence in ability to succeed in doing what I  want.

I have encountered progress in my relationship with people.

Self confidence and being at ease

My mentor enabled me to view  the world with more confidence and hope..

I felt important because I had a mentor who showed interest in me.

I felt relieved because I was able to share my fears