## Sheet1
Gezesso Water and Sanitation Project - HOPE International Development Agency | [6 empty] | 2016-06-01
|  | UNIT | QTY | RATE | TOTAL BUDGET | TOTAL BUDGET | TOTAL BUDGET
1 | PROGRAM/OPERATIONAL COST |  |  |  | in Eth Birr | in USD$ | in GBP£
1.1 | Materials
1.1.1 | GI pipes different size (6m long)
| 2 " | Pcs | 33 | 1615.14 | 53299.69 | 2505.0854 | 1705.5901
1.1.1.1 | 1 ½ “ | Pcs | 158 | 1245.99 | 196866.42 | 9252.7217 | 6299.7254
1.1.1.2 | 1 ¼ “ | Pcs | 281 | 1040.11 | 292270.91 | 13736.7328 | 9352.6691
1.1.1.3 | 1” | Pcs | 609 | 951 | 579156.56 | 27220.3583 | 18533.0099
1.1.2 | Cement for different construction | bags | 512.6021 | 325 | 166595.68 | 7829.997 | 5331.0618
1.1.3 | Reinforcement bars 6mm Ø | Kg | 373.01 | 57.1 | 21298.87 | 1001.0469 | 681.5638
1.1.4 | Reinforcement bars 8mm Ø | pcs | 85 | 144.98 | 12322.88 | 579.1754 | 394.3322
1.1.5 | Reinforcement bars 10mm Ø | pcs | 94 | 195.58 | 18384.71 | 864.0814 | 588.3107
1.1.6 | Chicken wire(1.8m * 30m) | roll | 5 | 670 | 3350 | 157.45 | 107.2
1.1.7 | Pipe fittings(16.5% of pipe cost) | Birr | Various | 168239 | 168239 | 7907.233 | 5383.648
1.1.8 | Sand | M3 | 119 | 1500 | 178500 | 8389.5 | 5712
1.1.9 | Gravel | M3 | 56 | 2600 | 145600 | 6843.2 | 4659.2
1.1.10 | Stone | M3 | 158 | 670 | 105860 | 4975.42 | 3387.52
1.1.11 | Anti-rust paint | Kg | 9 | 110 | 990 | 46.53 | 31.68
1.1.12 | Black wire | Kg | 62.5 | 60 | 3750 | 176.25 | 120
1.1.13 | Nails deferent size (7,9 & 10) each | Pack | 7 | 200 | 1400 | 65.8 | 44.8
1.1.14 | Equaliyptuse poles | No | 79 | 120 | 9480 | 445.56 | 303.36
1.1.15 | Water quality test/spring | No | 2 | 3625 | 7250 | 340.75 | 232
1.1.16 | Provision of maintenance tools & fittings for users | lump sum | lump sum | 60000 | 60000 | 2820 | 1920
1.1.18 | Timber | m2 | 27 | 310 | 8370 | 393.39 | 267.84
1.1.17 | Miscellaneous costs | lump sum | lump sum | 60000 | 60000 | 2820 | 1920
| Sub Total |  |  |  | 2092984.72 | 98370.2818 | 66975.511
1.2 | Materials & Labour Transport
1.2.1 | Project truck & Vehicles expenses | lump sum | lump sum | 270000 | 270000 | 12690 | 8640
1.2.2 | Rental trucks | lump sum | lump sum | 80000 | 80000 | 3760 | 2560
| Sub total |  |  |  | 350000 | 16450 | 11200
1.3 | Program Staff Salary & Benefits (Project Site Level)
1.3.1 | Project Officer | months | 3 | 12588 | 37764 | 1774.908 | 1208.448
1.3.2 | Hydrogeologist | months | 3 | 8592 | 25776 | 1211.472 | 824.832
1.3.3 | Construction Foreman | months | 3 | 7193.4 | 21580.2 | 1014.2694 | 690.5664
1.3.4 | Community Mobilizer | months | 15 | 5395.2 | 80928 | 3803.616 | 2589.696
1.3.5 | Truck Driver | months | 3 | 5262 | 15786 | 741.942 | 505.152
1.3.6 | Camping material & other related expenses | lump sum | lump sum | 20000 | 20000 | 940 | 640
1.3.7 | Medical expenses | months | 3 | 5000 | 15000 | 705 | 480
1.3.8 | Program staff camp allowance | lump sum | lump sum | 48000 | 48000 | 2256 | 1536
| Sub total |  |  |  | 264834.2 | 12447.2074 | 8474.6944
1.4 | Locally Hired Staff
1.4.1 | Truck driver assistant salary | months | 3 | 1300 | 3900 | 183.3 | 124.8
1.4.2 | Field worker clothes and supplies | lump sum | lump sum | 20000 | 20000 | 940 | 640
1.4.3 | Contractual labor (mason, plumber, etc.) | lump sum | lump sum | 255555.57 | 255555.57 | 12011.1118 | 8177.7782
1.4.4 | Assistant Community Educators (10 people working in 2016 and 5 will continue in 2017) | months | 13.5 | 7215 | 97402.5 | 4577.9175 | 3116.88
1.4.5 | On job train for caretakers & other technical staff | lump sum | lump sum | 7500 | 7500 | 352.5 | 240
| Sub total |  |  |  | 384358.07 | 18064.8293 | 12299.4582
1.5 | Water Committee Training
1.5.1 | Stationary (for all trainee /committee) | lump sum | lump sum | 6000 | 6000 | 282 | 192
1.5.2 | Training material & manuals and guide book | lump sum | lump sum | 4500 | 4500 | 211.5 | 144
1.5.3 | Per diem for trainee (committee) & other community members | lump sum | lump sum | 27450 | 27450 | 1290.15 | 878.4
1.5.4 | Tea break | lump sum | lump sum | 3900 | 3900 | 183.3 | 124.8
| Sub Total |  |  |  | 41850 | 1966.95 | 1339.2
| PROGRAM COST TOTAL |  |  |  | 3134026.99 | 147299.2685 | 100288.8637
2 | ADMIN COST |  | Qty | Rate | Total
2.1 | Admin Staff Salary & Benefits (in Addis Ababa)
2.1.1 | Country director | months | 4 | 36000 | 144000 | 6768 | 4608
2.1.2 | Finance Officer | months | 4 | 9924 | 39696 | 1865.712 | 1270.272
2.1.3 | Liaison & Logistics officer | months | 4 | 8592 | 34368 | 1615.296 | 1099.776
2.1.4 | Office cleaner & messenger | months | 4 | 2065.2 | 8260.8 | 388.2576 | 264.3456
2.1.5 | Medical expense | months | 4 | 7000 | 28000 | 1316 | 896
| Sub total |  |  |  | 254324.8 | 11953.2656 | 8138.3936
2.2 | Admin Staff Salary & Benefits (Field Office)
2.2.1 | Program Coordinator | months | 4 | 20580 | 82320 | 3869.04 | 2634.24
2.2.2 | Project Casher/Accountant | months | 4 | 5395.2 | 21580.8 | 1014.2976 | 690.5856
2.2.3 | Office Cleaner & Messenger | months | 4 | 2065.2 | 8260.8 | 388.2576 | 264.3456
2.2.4 | Guards at Field Office (3) - Salary & Benefits | months | 4 | 4730.4 | 18921.6 | 889.3152 | 605.4912
2.2.5 | Medical expenses | months | 4 | 4000 | 16000 | 752 | 512
| Sub total |  |  |  | 147083.2 | 6912.9104 | 4706.6624
2.3 | Monitoring & Evaluation, + network & experience sharing trips
2.3.1 | Monitoring & Evaluation, + network & experience sharing trips | months | 3 | 10000 | 30000 | 1410 | 960
| Sub total |  |  |  | 30000 | 1410 | 960
2.4 | Other Overhead Expenses
2.4.1 | Transport costs for head office | lump sum | lump sum | 15000 | 15000 | 705 | 480
2.4.2 | Stationery, cleaning equipment and materials | months | 3 | 3000 | 9000 | 423 | 288
2.4.3 | Utilities/water, electricity etc (Field Office and Addis Ababa office ) | months | 3 | 1500 | 4500 | 211.5 | 144
2.4.4 | Telephone, Postage, Fax, Internet etc (Field Office and Addis Ababa office ) | months | 3 | 10000 | 30000 | 1410 | 960
2.4.5 | Field Office & store rent | months |  | 0 | 0 | 0 | 0
2.4.6 | Membership fees, networking & experience sharing activities | lump sum | lump sum | 7500 | 7500 | 352.5 | 240
2.4.7 | Bank charges | months | 3 | 600 | 1800 | 84.6 | 57.6
| Sub total |  |  |  | 67800 | 3186.6 | 2169.6
| ADMIN COST TOTAL |  |  |  | 499208 | 23462.776 | 15974.656
| GRAND TOTAL |  |  |  | 3633234.99 | 170762.0445 | 116263.5197
| NB: Admin Costs as % of total | 13.74%