ACTION PLAN 2017-2018 / CENTRE MAREMBO

| AREA A: HEALTH |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SPECIFIC OBJECTIVE I. TO PROVIDE THE GIRLS WITH HEALTH CARE |  |  |  |  |  |  |  |  |  |  |  |  |
| RESULTS |  | INDICATORS |  | ACTIVITIES | TIME FRAMEWORK |  |  |  |  | BUDGET/IN USD |
|  |  |  |  |  | 1st Term | 2nd Term | 3rd Term | 4th Term |  |  |
| R.I.1. The girls are provided with prevention services |  | - Number of girls checked - Number of vaccinated girls. - Number of pregnant girls pre-screened. - Quantity of equipment purchased, |  | A.I.1. To make STD checks for the victims, | X | X | X | X |  | 32,000USD |
|  |  |  |  | A.I.2. To administer vaccinations | X | X | X | X |  |  |
|  |  |  |  | A.I.3. To make a pre-screening for teen and pre-teen pregnant. | X | X | X | X |  |  |
|  |  |  |  | A.I.4. To buy equipment for prevention of deseases (eg: buy mosquito nets to prevent malaria) | X | X | X | X |  |  |
| R I.2. The girls are provided with health care for various deseases |  | - Number of girls who have received medical treatment - Number of girls having chronic deseases followed up |  | A I.2.1. To provide health care for various deseases | X | X | X | X |  |  |
|  |  |  |  | A I.2.2. To make constant follow-ups for HIV/AIDS positive victims and other chronic deseases | X | X | X | X |  |  |
| R I.3. The girls helped with mental health/ Pscych support |  | - Number of girls participated in group counselling sessions and individual counselling sessions |  | A.3.1 Counseling sessions | X | X | X | X |  |  |
| AREA B : EDUCATION |  |  |  |  |  |  |  |  |  |  |  |  |
| SPECIFIC OBJECTIVE II. TO PROVIDE THE GIRLS WITH EDUCATION |  |  |  |  |  |  |  |  |  |  |  |  |
| RESULTS |  | INDICATORS | ACTIVITIES |  | TIME FRAMEWORK |  |  |  |  | BUDGET |
|  |  |  |  |  | 1st Term | 2nd Term | 3rd Term | 4th Term |  |  |
| R II.1. The girls have access to formal education |  | - Number of girlrs enrolled - Quantity of materials purchased and spent on amount fees | A II.1.1. To find schools for their enrollment |  | X | X | X | X |  | 20,000USD |
|  |  |  | A II.1.2. To find the school requirements ( school fees, uniforms, school books, transport fees etc.) |  | X | X | X | X |  |  |
| R II.2.Girls attend vocational training |  | - Number of girls enrolled - Quantity of materials purchased and amount spent on fees. | A II.2.1. To find the vocational training centers for enrollment |  | X | X | X | X |  |  |
|  |  |  | A II.2.2. To fulfill the requirements for VTCs |  | X | X | X | X |  |  |
| AREA C : PHYSIOLOGICAL NEEDS |  |  |  |  |  |  |  |  |  |  |  |  |
| SPECIFIC OBJECTIVE III. TO MEET TO THE PHYSIOLOGICAL NEEDS OF THE GILRS |  |  |  |  |  |  |  |  |  |  |  |  |
| RESULTS |  | INDICATORS | ACTIVITIES |  | TIME FRAMEWORK |  |  |  |  | BUDGET |
|  |  |  |  |  | 1st Term | 2nd Term | 3rd Term |  | 4th Term |  |
| R III.1. The girls and their babies have three meals a day. |  | - Quantity of food supplies purchased. | A III.1.1. To purchase food supplies |  | X | X | X |  | X |  |
|  |  |  | A III.1.2. To prepare meals |  | X | X | X |  | X |  |
| R III.2. The girls are provided with a safe home |  | - Amount of money paid for the rent - Number of the equipments purchased and renewed | A III.2.1. To pay a rent for the shelter |  | X | X | X |  | X | 45,000 |
|  |  |  | A III.2.2. To equip and renew the equipment of the safe home |  | X | X | X |  | X |  |
| R III.3. The Hygiene is provided to girls their surroundings |  | - Quantity of the hygiene products, equipment and the amount of money spent on them. | A III.2.3. To buy the hygienic products, clothes and equipment for the girls and their safe home |  | X | X | X |  | X |  |
|  |  |  | A III. 2.4. To clean the compound of the safe home. |  | X | X | X |  | X |  |
| AREA D : LEGAL AND JURDICIAL SUPPORT |  |  |  |  |  |  |  |  |  |  |  |  |
| SPECIFIC OBJECTIVE V : TO MENTOR THE VICTIMS OF GBV IN JURIDCTION |  |  |  |  |  |  |  |  |  |  |  |  |
| RESULTS | INDICATORS |  | ACTIVITIES |  | TIME FRAMEWORK |  |  |  |  | BUDGET/ IN USD |
|  |  |  |  |  | 1st Term | 2nd Term | 3rd Term |  | 4th Term |  |
| R V.1. The girls who are victims of sexual abuse receive juridicial mentoring | - Number of cases submitted to the courts - Number of perpetrators sentenced |  | A V.1.1. To find lawyers |  | X | X | X |  | X | 5,000 |
|  |  |  | A V.1.2. To submit the cases of abuse to the courts |  | X | X | X |  | X |  |
|  |  |  | A V.1. 3. To follow up the courts |  | X | X | X |  | X |  |
| AREA E : MANAGMENT AND ADMINISTRATION |  |  |  |  |  |  |  |  |  |  |  |
| SPECIFIC OBJECTIVE VI : TO MANAGE AND ADMINISTRATE THE IMPLEMENTATION OF THIS PROJECT |  |  |  |  |  |  |  |  |  |  |  |
| RESULTS | INDICATORS |  | ACTIVITIES |  | TIME FRAMEWORK |  |  |  |  | BUDGET/ IN USD |
|  |  |  |  |  | 1st Term | 2nd Term | 3rd Term |  | 4th Term |  |
| R VI.1. The implementation is realized | - The rate of achievement of realized activities |  | A.VI.1.1. To fulfil the actions as planned. A.VI.1.2. To conduct an M&E |  | X | X | X |  | X | 18,000 |